## Slide 1: Lacey Comprehensive Plan Update
Community Engagement and Branding

## Slide 2: Goals:
Build broad awareness about the Plan
Educate people about the Plan’s relevance
Encourage participation in the full process (“Soup to Nuts”)

## Slide 3: Communications Strategy
Goal: Implement an effective communications strategy to promote community engagement opportunities and build interest in the Comprehensive Plan.
Build awareness among hard-to-reach audiences.

## Slide 4: Hard to Reach Audiences
Youth and Young Adults (18-30)
Renters
Equity-priority Communities
Others

## Slide 5: Hard to Reach Audiences
Youth and Young Adults
  Prioritize online engagement (web, social media)
  Interactive educational games
  Events staged at popular locales
Renters
  Partner with large complexes/property management agencies
Equity-priority Communities
  Translated collateral
  Leverage cultural events
  Partner with local schools (reach parents through kids)

## Slide 6: Community Engagement
Collaborate with Local Community-Based Organizations
Inform Decision-Making
Leverage Existing Community Engagement Efforts
Identify Barriers to Participation
Create Opportunities for Inclusive and Equitable Participation
Build Long-Term Capacity for Civic Engagement around Planning and Development
Ensure accountability

## Slide 7: Community Engagement Phasing
Visioning
Community
Priorities
Draft Plan
Final Plan
Multiple opportunities for public engagement throughout the process…

## Slide 8: Community Engagement Phasing
Engagement efforts will align with Plan development phases:
  Visioning (Summer 2024)
  Community Priorities (Fall 2024)
  Draft Plan (Winter/Spring 2025)
  Final Plan (Spring/Summer 2025)

## Slide 9: Phase 1: Visioning
Host Citywide Community Visioning event
  Held at Library or City Hall
  Youth and family-friendly
  Engaging interactive exercises
Table at local events
  Night Market @ The Depot, etc.
Launch online community survey
  Promote via City website and social media

## Slide 10: Phase 2: Community Priorities
Focus on local neighborhood events/pop-ups
  Locations TBD
  Explore incentives (through CBOs, businesses, etc.)
Launch map-based survey targeting local communities
Conduct outreach through community partners
Educational outreach through local schools
Local business outreach (lunch & learn, e.g.)

## Slide 11: Phase 3: Draft Plan
Draft Plan Open House (in-person and virtual)
  Spring 2025
Interactive kiosks at Library/City Hall
Launch the web-based plan interface that provides high-level context and allows for user comments on policy directions
Continue outreach to community partners, schools, businesses, etc.

## Slide 12: Phase 4: Final Plan
The final Comprehensive Plan will be a web-based document that frames policies in an easy-to-understand way, allowing users to access the level of detail they want.
The Plan will also include printable PDFs for each chapter.

## Slide 13: Supporting Materials
Branded Collateral
  Print Material (brochures, invitations, etc.)
  Digital/Social Media Content
  Advertising (as needed)
Public Engagement Toolkit
  Facilitator’s Guide
  Activity materials w/ instructions
  Sign in sheet
Web Tools
  Visioning survey
  Map-based survey
  Interactive Plan

## Slide 14: Branding
We have a name!
Envision Tomorrow
Lacey Comprehensive Plan Update

## Slide 15: Logo Concepts

## Slide 16: Next Steps
Plan Branding
  Review logo concepts
  Develop brand style guide
Community Engagement Plan
  Draft expected the week of 5/19
  Target audience outreach strategies
Phase 1 Engagement: Preparation
  Plan Community Visioning Event
  Develop online survey instrument
  Prepare supplemental outreach materials